# DAILIES ROUND-UP

Name: Leo Park

Team: Video

Workstream: Q4 launch film

Date: Today

AI tool: Claude

## SUMMARY

Client notes are in and applied. The master and 30-second cutdown are rendering for delivery on Thursday.

## DONE

- Applied Priya’s notes: product hold extended by two frames before the cut

- Rebuilt the end card with the new URL and legal line

- Exported the 60s master in 4K ProRes for QC

## IN PROGRESS

- 30s cutdown edit, about 70% there

## BLOCKERS

- Music stems for the 30s version not received from the composer yet

## KEY TARGETS

- Deliver the master and 30s cutdown by Thursday noon

- QC pass on the 9:16 versions

## NOTES

- None

# DAILIES ROUND-UP

Name: Leo Park

Team: Video

Workstream: Subtitle automation

Date: Today

AI tool: Gemini

## SUMMARY

German subtitles now fit on vertical cuts using the agency’s shorter copy. The 32:9 export preset still needs a fix.

## DONE

- Imported the condensed German copy from the agency

- Re-timed German subtitles on all six vertical cutdowns

## IN PROGRESS

- Spot-checking line breaks on the 9:16 versions

## BLOCKERS

- Export preset still breaks on the 32:9 station loop; waiting on the tool vendor

## KEY TARGETS

- Sign off German on all vertical cuts Wednesday

- Re-export the station loop once the preset fix lands

## NOTES

- Agency confirmed they can supply condensed copy for Spanish too

# DAILIES ROUND-UP

Name: Leo Park

Team: Video

Workstream: Brand sting refresh

Date: Today

AI tool: ChatGPT

## SUMMARY

Kicked off the 5-second brand sting refresh with three motion directions ready for review.

## DONE

- Wrote three motion directions with ChatGPT: orbit, fold and light sweep

- Pulled reference frames for each direction into the team board

## IN PROGRESS

- Rough animatic for the orbit direction

## BLOCKERS

- None

## KEY TARGETS

- Styleframes for all three directions by Friday

- Pick one direction with Priya on Monday

## NOTES

- None